## Guide
IAC INTERNSHIP PROGRAM 2023
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Your Full Name
Document Created On: | DD-MMM-YYYY
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f

## PROJECT PLAN
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | Analyzing Student Attributes for Career Success |  |  | SAUMYA DEEP RAWAT
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Detailed Analysis Report,Data Visualization,Key Success Factors
PROJECT SCOPE | Descriptive Analysis,GPA Variation Among Colleges,Student Experience
PROJECT START DATE | 2023-08-01
PROJECT END DATE | 2023-08-13
OVERALL PROGRESS | COMPLETED
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2023-08-01 | 2023-08-02 | 2 | COMPLETED
| 1.2 Recruit a team |  | 2023-08-01 | 2023-08-02 | 2 | COMPLETED
| 1.3 Create a project charter |  | 2023-08-01 | 2023-08-02 | 2 | COMPLETED
| 1.4 Requirement gathering |  | 2023-08-01 | 2023-08-02 | 2 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2023-08-03 | 2023-08-03 | 1 | COMPLETED
| 2.2 Baseline project plan |  | 2023-08-03 | 2023-08-03 | 1 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2023-08-03 | 2023-08-03 | 1 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2023-08-04 | 2023-08-04 | 7 | COMPLETED
| 3.2 Build |  | 2023-08-04 | 2023-08-04 | 7 | COMPLETED
| 3.2.1 Data Cleaning |  | 2023-08-05 | 2023-08-05 | 1 | COMPLETED
| 3.2.2 Q1-4 |  | 2023-08-06 | 2023-08-06 | 1 | COMPLETED
| 3.2.2 Q5-8 |  | 2023-08-07 | 2023-08-07 | 1 | COMPLETED
| 3.2.2 Q9-11 |  | 2023-08-08 | 2023-08-08 | 1 | COMPLETED
| 3.2.2 Q12-15 |  | 2023-08-09 | 2023-08-09 | 1 | COMPLETED
| 3.2.2 Q16-18 |  | 2023-08-10 | 2023-08-10 | 1 | COMPLETED
| 3.3 Testing |  | 2023-08-10 | 2023-08-10 | 1 | COMPLETED
| 4 Closure |  | 2023-08-13 | 2023-08-13 | 3 | COMPLETED